## January 13
| Data Available | MNF info from LO | Factor info from Allergan | Data Delivery | Comments
Finland | 4th February 2013 |  |  | 4th February 2013
Norway | 5th February 2013 |  |  | 5th February 2013
Sweden | 5th February 2013 |  | 6th February 2013 | 13th February 2013
Portugal | 8th February 2013 |  |  | 15th February 2013 | Data Availability was not confirmed from LO
Austria | 21st February 2013 |  |  | 25th February 2013 (Monday) | 21st Feb was Govt Holiday in Dhaka and we started the process on 22nd (Friday)
Netherlands | 14th February 2013 |  |  | 18th February 2013 (Monday) | Input data was available at late night of 14th Feb, process was started on 15th Feb (Friday)
Ireland | 20th February 2013 |  |  | 27th February 2013 | Late delivery because NI data comes late and also UK RSA data comes paralelly
Switzerland | 26th February 2013 |  |  | 27th February 2013
Luxembourg | 23rd February 2013 (Saturday) |  |  | 25th February 2013 (Monday)
Belgium | 23rd February 2013 (Saturday) |  |  | 25th February 2013 (Monday)
UK RSA | 20th February 2013 |  |  | 27th February 2013 | Late delivery Ireland, Luxembourg and Belgium data comes paralelly
Spain | 28th February 2013 |  |  | 13th March 2013 | Late delivery because Confirmation required for New Structure delivery
Italy | 28th February 2013 |  |  | 1st March 2013
France | 25th February 2013 |  |  | 6th March 2013 | Late Delivery because confirmation required for Updated Pack Information for pack description "_Inconnu"
UK HPA | 12th March 2013 |  |  | 18th March 2013 (Monday) | Rerun Data was available 12th Mar, Rerun data delivery confirmation from Carolina 15th Mar (Friday)
Germany | 5th March 2013 |  |  | 7th March 2013 | Data available from LO at Late night of 5th Mar, process started at 6th Mar
UK PBS | 18th March 2013 |  |  | 21st March 2013

## February 13
| Data Available | MNF info from LO | Factor info from Allergan | Data Delivery | Comments
Finland | 4th March 2013 | 11th March 2013 | 11th March 2013 | 22nd March 2013 | Late Delivery due to confirmation required for Optive data loading from Client and LO
Norway | 4th March 2013 |  |  | 6th March 2013
Sweden | 5th March 2013 |  | 11th March 2013 | 12th March 2013 | Late Delivery because Factor information comes late from Client
Portugal | 7th March2013 |  |  | 8th March2013
Austria | 22nd March2013 |  |  | 22nd March2013
Netherlands | 15th March2013 (Friday) |  |  | 18th March 2013 (Monday)
Ireland | 20th March 2013 | 25th March 2013 | 22nd March 2013 | 27th March 2013 | Late Delivery because Factor nad MNF information comes late from Client and LO
Switzerland | 20th March2013 |  |  | 21st March2013
Luxembourg | 25th March2013 |  |  | 27th March2013
Belgium | 21st March2013 |  |  | 25th March2013 | Late Delivery because Parallel process run for Ireland, Luxembourg, Switzerland
UK RSA | 20th March2013 |  |  | 27th March2013 | Late Delivery because Parallel process run for Ireland, Spain, Italy
Spain | 26th March2013 |  |  | 27th March2013
Italy | 26th March2013 |  |  | 27th March2013
France | 25th March2013 |  |  | 28th March2013
UK HPA | 31st March2013 |  |  | 01st April 2013
Germany | 08th March2013 |  |  | 09th April 2013 | Late Delivery because input Source data was late from LO
UK PBS | 31st March 2013 |  |  | 8th April 2013

## March 13
| Data Available | MNF info from LO | Factor info from Allergan | Data Delivery | Comments
Finland | 3rd April 2013 | 4th April 2013 | 4th April 2013 | 4th April 2013 | Deliver on time
Norway | 3rd April 2013 | 4th April 2013 | 4th April 2013 | 4th April 2013 | Deliver on time
Sweden | 4th April 2013 (Thursday) |  | 5th April 2013 (Friday) | 8th April 2013 (Monday) | Late Delivery
Portugal | 9th April 2013 |  |  | 10th April 2013 | Deliver on time, Rerun Data Delivered on 30th April,2013
Austria | 11th April 2013 |  |  | 11th April 2013 | Deliver on time
Netherlands | 16th April 2013 |  |  | 18th April 2013 | Late Delivery Due to Server Link Problem
Ireland | 23rd April 2013 |  |  | 14th May 2013 | Delivered
Switzerland | 19th April 2013 (Friday) |  |  | 22nd April 2013 | Late Delivery Due to Server Link Problem
Luxembourg | 23rd April 2013 |  |  | 29th April 2013 | Late Delivery Due to Server Link Problem
Belgium | 18th April 2013 | 19th April 2013 | 19th April 2013 | 19th April 2013 | Deliver on time
UK RSA | 23rd April 2013 |  |  | 10th May 2013 | Delivered
Spain | 24th April 2013 |  |  | 30th April 2013 | Delivery Delayed due to other country production run
Italy | 30th April 2013 |  |  | 30th April 2013 | Deliver on Time
France | 24th April 2013 |  |  | 26th April 2013 | Deliver on Time
UK HPA | 29th April 2013 |  |  | 3rd May 2013 | Delivery Delayed due to Confirmation from LO
Germany | 26th April 2013 (Friday) |  |  | 30th April 2013 | Delivery Delayed due to other country production run
UK PBS | 27th April 2013 (Saturday) |  |  |  | Input Data Issue
Delivered
Production Process Going
Data Available, Waiting to be processed
Data Not Available

## April 13
| Data Available | MNF info from LO | Factor info from Allergan | Data Delivery | Comments
Finland | 4th May 2013 (Saturday) |  |  | 6th May 2013 | Deliver on time
Norway | 3rd May 2013 (Friday) | 6th May 2013 | 7th May 2013 | 7th May 2013 | Deliver on time
Sweden | 6th May 2013 |  | 7th May 2013 | 7th May 2013 | Deliver on time
Portugal | 8th May 2013 |  |  | 9th May 2013 | Deliver on time
Austria | 15th May 2013 |  |  | 15th May 2013 | Deliver on time
Netherlands | 18th May 2013 (Saturday) |  |  | 20th May 2013 | Deliver on time
Ireland | 4th June 2013 |  |  | 6th June 2013 | Delivered Late due to Input data Availability from LO
Switzerland | 22nd May 2013 |  |  | 24th May 2013 | Deliver on time
Luxembourg | 30th May 2013 | 30th May 2013 | 30th May 2013 | 30th May 2013 | Delivered Late due to Input data Availability from LO
Belgium | 30th May 2013 | 31st May 2013 | 31st May 2013 | 31st May 2013 | Delivered Late due to Input data Availability from LO
UK RSA | 30th May 2013 |  |  | 31st May 2013 | Delivered Late due to Input data Availability from LO
Spain | 3rd June 2013 | 4th June 2013 |  | 4th June 2013 | Delivered Late due to Input data Availability from LO
Italy | 27th May 2013 |  |  | 28th May 2013 | Deliver on time
France | 22nd May 2013 |  |  | 24th May 2013 | Deliver on time
UK HPA 05 | 29th May 2013 |  |  | 30th May 2013 | Deliver on time
UK HPA 07 | 29th May 2013 |  |  | 13th June 2013 | Production process error. Redelivery
Germany | 28th May 2013 |  |  | 29th May 2013 | Deliver on time
UK PBS
Delivered
Production Process Going
Data Available, Waiting to be processed
Data Not Available

## May 13
| Data Available | MNF info from LO | Factor info from Allergan | Data Delivery | Comments
Finland | 4th June 2013 | 4th June 2013 | 4th June 2013 | 5th June 2013 | Deliver on time
Norway | 6th June 2013 |  | 6th June 2013 | 7th June 2013 | Delivered Late due to Input data Availability from LO
Sweden | 5th June 2013 |  | 6th June 2013 | 6th June 2013 | Deliver on time
Portugal | 12th June 2013 |  |  | 13th June 2013 | Deliver on time
Austria | 12th June 2013 |  |  | 13th June 2013 | Deliver on time
Netherlands | 17th June 2013 |  |  | 19th June 2013 | Deliver on time
Ireland | 19th June 2013 |  |  | 20th June 2013 | Deliver on time
Switzerland | 19th June 2013 |  |  | 20th June 2013 | Deliver on time
Luxembourg | 25th June 2013 |  |  | 27th June 2013 | Delivered Late due to Input data Availability and format from LO
Belgium | 19th June 2013 | 20th June 2013 | 20th June 2013 | 21st June 2013 | Deliver on time
UK RSA | 4th July 2013 |  |  | 8th July 2013 | Delivered Late due to Input data Availability from LO and Rerun
Spain | 24th June 2013 |  |  | 1st July 2013 | Delivered Late due to parallel Production process running
Italy | 27th June 2013 |  |  | 28th June 2013 | Deliver on time
France | 25th June 2013 |  |  | 26th June 2013 | Deliver on time
UK HPA 05 | 28th June 2013 |  |  | 1st July 2013 | Delivered Late due to Input data Confirmation from LO
UK HPA 07 | 4th July 2013 |  |  | 8th July 2013 | Delivered Late due to Input data Availability from LO and Rerun
Germany | 26th June 2013 |  |  | 28th June 2013 | Deliver on time
UK PBS
Delivered
Production Process Going
Data Available, Waiting to be processed
Data Not Available

## June 13
| Data Available | MNF info from LO | Factor info from Allergan | Data Delivery | Comments
Finland | 2nd July 2013 |  |  | 4th July 2013 | Deliver on time
Norway | 2nd July 2013 | 3rd July 2013 | 3rd July 2013 | 4th July 2013 | Deliver on time
Sweden | 3rd July 2013 |  | 4th July 2013 | 4th July 2013 | Deliver on time
Portugal | 8th July 2013 |  |  | 9th July 2013 | Deliver on time
Austria | 10th July 2013 | 11th July 2013 |  | 12th July 2013 | Deliver on time
Netherlands | 16th July 2013 |  |  | 16th July 2013 | Deliver on time
Ireland | 15th July 2013 |  |  | 16th July 2013 | Deliver on time
Switzerland | 17th July 2013 | 18th July 2013 | 18th July 2013 | 18th July 2013 | Deliver on time
Luxembourg | 23rd July 2013 |  |  | 24th July 2013 | Deliver Delay due to Data Availability from LO
Belgium | 17th July 2013 |  |  | 18th July 2013 | Deliver on time
UK RSA | 22nd July 2013 |  |  | 26th July 2013 | Deliver on time
Spain | 25th July 2013 |  |  | 26th July 2013 | Deliver on time
Italy | 24th July 2013 |  |  | 26th July 2013 | Deliver on time
France | 23rd July 2013 |  |  | 26th July 2013 | Deliver on time
UK HPA 05 | 26th July 2013 |  |  | 29th July 2013 | Deliver on time
UK HPA 07 | 26th July 2013 |  |  | 31st July 2013 | Deliver on time
Germany | 30th July 2013 |  |  | 31st July 2013 | Deliver on time
Delivered
Production Process Going
Data Available, Waiting to be processed
Data Not Available

## July 13
| Data Available | MNF info from LO | Factor info from Allergan | Data Delivery | Comments
Finland | 2nd August 2013 | 8th August 2013 | 5th August 2013 | 12th August 2013 | Delay Delivery 7 Days
Norway | 2nd August 2013 | 6th August 2013 | 5th August 2013 | 7th August 2013 | Delay Delivery 2 Days
Sweden | 5th August 2013 | 6th August 2013 |  | 7th August 2013 | Deliver on Time
Portugal | 8th August 2013 |  |  | 12th August 2013 | Deliver on Time
Austria | 13th August 2013 |  |  | 13th August 2013 | Deliver on Time
Netherlands | 14th August 2013 |  |  | 14th August 2013 | Deliver on Time
Ireland | 19th August 2013 |  |  | 27th August 2013 | Redelivery
Switzerland | 21st August 2013 |  |  | 22nd August 2013 | Deliver on Time
Luxembourg | 26th August 2013 |  |  | 26th August 2013 | Deliver on Time
Belgium | 16th August 2013 |  |  | 16th August 2013 | Deliver on Time
UK RSA | 23rd August 2013 (FRI) |  |  | 26th August 2013(MON) | Deliver on Time
Spain | 27th August 2013 |  |  | 29th August 2013 | Deliver on Time
Italy | 28th August 2013 |  |  | 2nd September 2013 | Delay Delivery 2 Days Due to FTP problem
France | 23rd August 2013 (FRI) |  |  | 27th August 2013 | Deliver on Time
UK HPA 05 | 29th August 2013 |  |  | 30th August 2013 | Deliver on Time
UK HPA 07 | 29th August 2013 |  |  | 30th August 2013 | Deliver on Time
Germany | 27th August 2013 |  |  | 29th August 2013 | Deliver on Time
Delivered
Production Process Going
Data Available, Waiting to be processed
Data Not Available

## August 13
| Data Available | MNF info from LO | Factor info from Allergan | Data Delivery | Comments
Finland | 3rd September 2013 |  |  | 3rd September 2013 | Deliver on Time
Norway | 3rd September 2013 | 6th September 2013 | 4th September 2013 | 6th September 2013 | Delay Delivery due to MNF Information from LO
Sweden | 4th September 2013 |  | 5th September 2013 | 5th September 2013 | Deliver on Time
Portugal | 10th September 2013 |  |  | 10th September 2013 | Deliver on Time
Austria | 12th September 2013 |  |  | 12th September 2013 | Deliver on Time
Netherlands | 13th September 2013 |  |  | 16th September 2013 | Deliver on Time
Ireland | 16th September 2013 |  |  | 17th September 2013 | Deliver on Time
Switzerland | 18th Septemebr 2013 |  |  | 19th Septemebr 2013 | Deliver on Time
Luxembourg | 18th September 2013 |  |  | 30th September 2013 | Delay Delivery due to due to input data availability confirmation from LO
Belgium | 18th Septemebr 2013 |  |  | 19th Septemebr 2013 | Re-Delivered due to new pack information
UK RSA
Spain | 26th September 2013 |  |  | 30th September 2013 | Deliver on Time
Italy | 26th September 2013 |  |  | 30th September 2013 | Deliver on Time
France
UK HPA 05 | 26th September 2013 |  |  | 27th September 2013 | Deliver on Time
UK HPA 07 | 26th September 2013 |  |  | 27th September 2013 | Deliver on Time
Germany
Delivered
Production Process Going
Data Available, Waiting to be processed
Data Not Available